## Checklist
ESA Fulfillment Checklist — The Client Journey (A → Z) · 165-task build template
Status | Phase | Timeline | Task | Owner | Track
| 1 · Onboarding & Access | Day 0–2 | Signed agreement + payment confirmed | Both
| 1 · Onboarding & Access | Day 0–2 | Sale logged: summary, commission, offer + sales-call notes handed to fulfillment | Sales | Sales
| 1 · Onboarding & Access | Day 0–2 | Client pulled into the onboarding pipeline (triggers welcome) | Tech
| 1 · Onboarding & Access | Day 0–2 | Welcome email sent + kickoff call scheduled | CSM
| 1 · Onboarding & Access | Day 0–2 | Onboarding form sent + completed | Client
| 1 · Onboarding & Access | Day 0–2 | Marketing / Onboarding Survey completed → triggers team notification | Client | Mktg
| 1 · Onboarding & Access | Day 0–2 | Sales / offer intake completed (current offer, price, sales process, team size) | Client | Sales
| 1 · Onboarding & Access | Day 0–2 | Grant Skool access — invite client + their team to the ESA portal/community | CSM
| 1 · Onboarding & Access | Day 0–2 | Kickoff call held | Both
| 1 · Onboarding & Access | Day 0–2 | Access collected LIVE: GHL, domain/DNS, Stripe, Meta ad account, calendar | Client
| 1 · Onboarding & Access | Day 0–2 | A2P business details collected (legal entity, EIN, address, sample msgs) | Client
| 1 · Onboarding & Access | Day 0–2 | Read access to Stripe / checkout confirmed (for attribution) | Client
| 1 · Onboarding & Access | Day 0–2 | Slack channel + client ClickUp board set up | CSM
| 1 · Onboarding & Access | Day 0–2 | Scope confirmed out loud — what's in / what's NOT | CSM
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Confirm event topic + core messaging | Both
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Confirm event date & time (+ platform/link or venue) | Client
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Confirm the offer & pricing presented at the event | Client
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Define target audience / ICP | Both
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Build the Ultimate Target Audience Profile (TAP) | Ads | Mktg
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Internal review + approve the TAP | Ads | Mktg
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Send TAP to client → client approves (GATE before creative) | Both | Mktg
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Collect brand assets (logo, colors, fonts) | Client
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Collect testimonials, images, media (folder link) | Client
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Collect headshots + speaker photos (for flyers/posters) | Client | Mktg
| 2 · Discovery, Assets & Target Audience | Day 1–3 | Confirm VSL — or schedule scripting | Both
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Audit existing setup (only if migrating a CRM/GHL) | Tech
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Create GHL sub-account (business details + team) | Tech
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | SUBMIT A2P 10DLC — Day 2, the 72hr+ clock starts now | Tech
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Purchase phone number | Client
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Import + customize snapshot (tags, pipelines, workflows, triggers, fields) | Tech
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Create pipeline stages + disposition dropdowns | Tech
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Connect domain (funnel) | Client
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Connect subdomain + SPF/DKIM/DMARC (deliverability) | Client
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Create / choose Meta ad account + confirm ESA access | Ads | Mktg
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Create / choose FB Page; connect to GHL | Ads | Mktg
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Client adds payment method to the ad account | Client | Mktg
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Install Meta Pixel + custom events (Opt-In + Purchase) | Ads | Mktg
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Provide old leads → upload + clean into GHL | Both
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Build smart lists of hot leads to re-engage | Tech
| 3 · Tech Setup, A2P & Ad Accounts | Day 2–5 | Set up calendars + booking links for sales calls | Tech | Sales
| 4 · Funnel Build | Day 4–10 | Build registration / opt-in form + connect to funnel | Funnel
| 4 · Funnel Build | Day 4–10 | Build registration, confirmation & replay pages | Funnel
| 4 · Funnel Build | Day 4–10 | Build FB Lead Form + map into GHL with opt-in automations | Ads + Tech | Mktg
| 4 · Funnel Build | Day 4–10 | Build sales / booking page for the offer call | Funnel | Sales
| 4 · Funnel Build | Day 4–10 | Apply brand, testimonials & VSL | Funnel
| 4 · Funnel Build | Day 4–10 | Install website chat widget | Tech
| 4 · Funnel Build | Day 4–10 | Optimize for mobile + conversion | Funnel
| 4 · Funnel Build | Day 4–10 | Share draft with client → client approval (within 48h) | Both
| 4 · Funnel Build | Day 4–10 | Implement revisions; confirm domain + final approval | Both
| 4 · Funnel Build | Day 4–10 | Publish funnel live | Tech
| 4 · Funnel Build | Day 4–10 | Configure tracking — pixel, GA4, conversion events | Tech
| 4 · Funnel Build | Day 4–10 | Full end-to-end QA — register as a test lead; every email/text fires | Tech
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Import + configure automation snapshot | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Confirmations + internal notifications + SMS opener | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Reminder sequence | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Nurture sequence | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Re-engagement / reactivation (begins T-14) | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | No-show automation | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Replay automation | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Pipeline stage-change + post-purchase (buyer) automations | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | DNC / compliance automations (honors opt-outs) | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Booking calendar + video integration for sales calls | Tech | Sales
| 5 · Automations, Nurture & AI Agent | Day 10–14 | BUILD + TRAIN the AI Conversation Agent (reactivation / nurture / post-purchase) | Tech
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Speed-to-lead — instant text to new leads + rep alerts | Auto
| 5 · Automations, Nurture & AI Agent | Day 10–14 | Test every workflow end-to-end | Tech
| 6 · Content & Ad Creative | Day 12–15 | Generate nurture + re-engagement copy | Content
| 6 · Content & Ad Creative | Day 12–15 | Generate confirmation, reminder, no-show & replay copy | Content
| 6 · Content & Ad Creative | Day 12–15 | Send all email/SMS copy to client → approve (within 48h) | CSM
| 6 · Content & Ad Creative | Day 12–15 | Load approved content into all automations + re-test | Auto
| 6 · Content & Ad Creative | Day 12–15 | Write 5 ad copies → approve top 3 | Ads | Mktg
| 6 · Content & Ad Creative | Day 12–15 | Write 20 video scripts (Hook / Body / CTA) → approve top 10 | Ads | Mktg
| 6 · Content & Ad Creative | Day 12–15 | Write VSL script (if applicable) | Ads | Mktg
| 6 · Content & Ad Creative | Day 12–15 | Send full creative package to client for approval | CSM | Mktg
| 6 · Content & Ad Creative | Day 12–15 | Send filming Loom → client records + uploads raw footage (notify in Slack) | Client | Mktg
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | Edit ads & VSL from footage + brand colors → internal approve → client approves | Editor | Mktg
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | Create 50 static ad variations → client selects top 20 | Ads | Mktg
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | Design event flyer + speaker posters from headshots | Editor | Mktg
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | Build audiences: 20 warm (engagers + visitors), cold interests (15–20), custom + lookalikes | Ads | Mktg
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | SMS blast / email invitation to the database | Auto
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | Reactivation outreach to old leads (T-14) | Auto
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | PRE-LAUNCH CHECK: copy + ads + VSL approved; audiences built; funnel + automations live; pixel firing; ad access + payment set | Ads | Mktg
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | Launch — Campaign 1: Lead Conversion → Registration Page | Ads | Mktg
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | Launch — Campaign 2: FB Form Lead campaign (GHL form + opt-in automations) | Ads | Mktg
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | Launch — Campaign 3: Purchase Conversion → Purchase Page | Ads | Mktg
| 7 · Creative Build, Promotion & Ad Launch | Day 15–20 | Go live on the client's own ad account (T-7); track CPL / registrations daily | Ads | Mktg
| 8 · Sales System & Enablement | Day 7–18 | Review the client's current offer, price & guarantee | Both | Sales
| 8 · Sales System & Enablement | Day 7–18 | Structure the offer for the event (stack, bonuses, price, payment plans) | Both | Sales
| 8 · Sales System & Enablement | Day 7–18 | Build the sales / closing script for the event offer | Sales | Sales
| 8 · Sales System & Enablement | Day 7–18 | Build the objection-handling guide (top 10 objections) | Sales | Sales
| 8 · Sales System & Enablement | Day 7–18 | Build the sales presentation / pitch deck | Sales | Sales
| 8 · Sales System & Enablement | Day 7–18 | Build the order form / checkout in GHL (offer + payment plans) | Tech | Sales
| 8 · Sales System & Enablement | Day 7–18 | Set up the sales pipeline + dispositions for closers | Tech | Sales
| 8 · Sales System & Enablement | Day 7–18 | Configure Rex (AI sales agent) for speed-to-lead + booking | Tech | Sales
| 8 · Sales System & Enablement | Day 7–18 | Set up commission / comp tracking for the client's reps | Sales | Sales
| 8 · Sales System & Enablement | Day 7–18 | Define the day-of closer plan (ESA closers + AI support) | Sales | Sales
| 8 · Sales System & Enablement | Day 7–18 | Build the follow-up / closing cadence for non-buyers | Sales | Sales
| 8 · Sales System & Enablement | Day 7–18 | Confirm CRM access for the sales team + lead routing | Tech | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Grant the client's sales team Skool access + assign training modules | CSM | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Assign the ESA sales fundamentals course (Skool) | Sales | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Walk the team through the offer, script & objection guide | Sales | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Live role-play / practice closes with the client's reps | Sales | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Train on the CRM, pipeline + disposition discipline | Sales | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Train on speed-to-lead + follow-up standards | Sales | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Review recorded role-plays + give feedback | Sales | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Certify reps event-ready (sign-off) | Sales | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Confirm day-of roles: who closes, who supports, who tracks | Both | Sales
| 9 · Sales Training & Team Readiness | Day 14 → event | Final sales-readiness check before event | Sales | Sales
| 10 · Optimization & Pacing | Ongoing → event | DAILY: optimize creative / audiences / budget — kill losers, scale winners | Ads | Mktg
| 10 · Optimization & Pacing | Ongoing → event | DAILY data report: CPL, registrations, show rate, conversions, ROAS | Data | Mktg
| 10 · Optimization & Pacing | Ongoing → event | Optimize the AI agent's responses + flows (weekly QA) | Tech
| 10 · Optimization & Pacing | Ongoing → event | Build + run the 'Yes' campaign to qualify unresponsive leads | Auto
| 10 · Optimization & Pacing | Ongoing → event | Refine email/SMS copy off lead responses + data | Content
| 10 · Optimization & Pacing | Ongoing → event | Funnel improvements off conversion data; A/B test | Funnel
| 10 · Optimization & Pacing | Ongoing → event | Audit lead quality; clean + re-segment | Data
| 10 · Optimization & Pacing | Ongoing → event | Pacing check vs registration goal; adjust spend | Ads | Mktg
| 10 · Optimization & Pacing | Ongoing → event | WEEKLY: Data team reports the numbers (regs, show rate, CPL, conversions) | Data
| 11 · The Room — Event Day | Event day | Final tech check with client / host | Both
| 11 · The Room — Event Day | Event day | Verify day-of reminders firing; pause all promo automations | Tech
| 11 · The Room — Event Day | Event day | Confirm webinar link / venue + AV tested | Both
| 11 · The Room — Event Day | Event day | Brief the closing team + assign attendees / leads | Sales | Sales
| 11 · The Room — Event Day | Event day | Monitor live registrations / attendance | Data
| 11 · The Room — Event Day | Event day | Provide live support during the event | Both
| 11 · The Room — Event Day | Event day | Offer made from the stage / screen | Both
| 11 · The Room — Event Day | Event day | Closers + AI agent work the room / chat in real time | Sales | Sales
| 11 · The Room — Event Day | Event day | Capture order forms / payments live | Sales | Sales
| 11 · The Room — Event Day | Event day | Capture / save the recording for replay | Client
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | Trigger replay automation + replay email (T+0–1) | Auto
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | Follow-up sequence — attendees vs no-shows | Auto
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | Activate booking / sales-call automation for the offer | Auto
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | AI agent + closers work non-buyers (days 8–10 = peak window) | Sales | Sales
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | Closers run booked sales calls; log dispositions | Sales | Sales
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | Move buyers into purchased pipeline + post-purchase automations | Auto
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | Sales tracked in GHL — NO outside checkout (protects attribution) | Data
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | Reconcile sales + commissions with the client's team | Sales | Sales
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | ✦ CLIENT COLLECTING REVENUE — confirm payments / wires in | CSM
| 12 · Post-Event → CLIENT COLLECTS | T+0 to T+30 | Wind down / pause ads | Ads | Mktg
| 13 · Reporting & Client Success | Weekly + post-event | Daily scorecard delivered to the ops call | Data
| 13 · Reporting & Client Success | Weekly + post-event | Weekly client report compiled (Kim & Kim → Michaela) | Data
| 13 · Reporting & Client Success | Weekly + post-event | Weekly report delivered in Slack by Michaela | CSM
| 13 · Reporting & Client Success | Weekly + post-event | Friday update: what was completed + the numbers | CSM
| 13 · Reporting & Client Success | Weekly + post-event | Weekly 1:1 call with client (first 30 days, then as needed) | CSM
| 13 · Reporting & Client Success | Weekly + post-event | Celebrate client wins (shout-outs, milestones) | CSM
| 13 · Reporting & Client Success | Weekly + post-event | Log issues / escalations; loop in the right owner | CSM
| 13 · Reporting & Client Success | Weekly + post-event | Post-event results report (within 48h) | Data
| 13 · Reporting & Client Success | Weekly + post-event | Full performance report — regs, show rate, sales, ROAS | Data
| 13 · Reporting & Client Success | Weekly + post-event | Confirm the next-step plan with the client | CSM
| 14 · Renewal & Ascension | 30 days before contract end | RENEWAL conversation — start 30 days before contract end; tie window to event date | CSM
| 14 · Renewal & Ascension | 30 days before contract end | Present results + the case for the next engagement | Both
| 14 · Renewal & Ascension | 30 days before contract end | Offer ascension: ongoing webinars ($3K/mo), ads + data ($2,500/mo), or live event | CSM | Sales
| 14 · Renewal & Ascension | 30 days before contract end | Collect testimonial + case-study assets | CSM
| 14 · Renewal & Ascension | 30 days before contract end | Ask for referrals / warm intros | CSM | Sales
| 14 · Renewal & Ascension | 30 days before contract end | Sign the next engagement / start the recurring | Both | Sales
| 14 · Renewal & Ascension | 30 days before contract end | Update the pipeline + ladder for the renewal | Tech
| 15 · Off-boarding & Handover | At contract end (no renewal) | Off-boarding decision confirmed (not renewing) | CSM
| 15 · Off-boarding & Handover | At contract end (no renewal) | Schedule + hold the off-boarding call | CSM
| 15 · Off-boarding & Handover | At contract end (no renewal) | Final performance + results report delivered | Data
| 15 · Off-boarding & Handover | At contract end (no renewal) | Export client data (leads, contacts, reports, recordings) | Tech
| 15 · Off-boarding & Handover | At contract end (no renewal) | Hand over assets (funnel, creative, copy, recordings) | Tech
| 15 · Off-boarding & Handover | At contract end (no renewal) | Transfer or revoke access per agreement (GHL, Meta, domain) | Tech
| 15 · Off-boarding & Handover | At contract end (no renewal) | Reclaim ESA assets / remove ESA-owned integrations | Tech
| 15 · Off-boarding & Handover | At contract end (no renewal) | Final invoice + settle all payments | Data
| 15 · Off-boarding & Handover | At contract end (no renewal) | Exit survey + final testimonial request | CSM
| 15 · Off-boarding & Handover | At contract end (no renewal) | Revoke or move Skool access to alumni | CSM
| 15 · Off-boarding & Handover | At contract end (no renewal) | Remove from active boards; archive client folder + Slack | CSM
| 15 · Off-boarding & Handover | At contract end (no renewal) | Referral / future re-engagement ask | CSM | Sales

## Phases
Phases — gates & owners
# | Phase | Timeline | Phase Owner | Gate to Advance | Tasks
1 | Onboarding & Access | Day 0–2 | CSM | Access in hand + scope confirmed out loud | 14
2 | Discovery, Assets & Target Audience | Day 1–3 | Both | Topic, offer, date, assets & TAP approved | 11
3 | Tech Setup, A2P & Ad Accounts | Day 2–5 | Tech | A2P submitted + GHL & Meta stack connected | 15
4 | Funnel Build | Day 4–10 | Funnel | Funnel live + full QA passed | 12
5 | Automations, Nurture & AI Agent | Day 10–14 | Auto | All automations tested + AI agent live | 13
6 | Content & Ad Creative | Day 12–15 | Content + Ads | Nurture content + ad creative approved | 9
7 | Creative Build, Promotion & Ad Launch | Day 15–20 | Ads | Ads live + outreach loaded | 11
8 | Sales System & Enablement | Day 7–18 | Sales | Offer, scripts, deck & sales pipeline built | 12
9 | Sales Training & Team Readiness | Day 14 → event | Sales | Client's team certified event-ready | 10
10 | Optimization & Pacing | Ongoing → event | Ads + Data | Pacing to registration goal | 9
11 | The Room — Event Day | Event day | Both | Event delivered + offer made + sales captured | 10
12 | Post-Event → CLIENT COLLECTS | T+0 to T+30 | Auto + Sales + CSM | Client collecting + revenue attributed in GHL | 10
13 | Reporting & Client Success | Weekly + post-event | CSM + Data | Client informed + results reported | 10
14 | Renewal & Ascension | 30 days before contract end | CSM | Next engagement signed or recurring started | 7
15 | Off-boarding & Handover | At contract end (no renewal) | CSM + Tech | Data exported, access settled, client archived | 12

## Legend & Rules
Ground rules — the 3 that protect every build
A2P starts Day 0–2 | The 72hr+ approval clock is the bottleneck — submit it before anything else.
Client deadlines are real | Access, assets, approvals due fast. A client delay moves THEIR date day-for-day — not ours.
Everything tracked in GHL | No outside checkout or landing pages — that's what lets Data measure and prove ROI.
Owners
CSM | Michaela
Tech | Shah
Funnel | Hamza
Auto | Jawad
Ads | Mal / Zoe
Content | Sohaib
Editor | video editor
Sales | Emanuela / closers
Data | Kim & Kim
Client | the client
Both | joint
Track tags
Mktg | marketing track
Sales | sales track